## Sheet1
List of tasks, the Quark, winter 2019/20
done | task | comment
√ | fill, trim motor mount fairings
√ | paint motor mount fairings
√ | improve riveting, fill, paint cowling
√ | replace BMS board
√ | test power train | all better. BMS board was the culprit.
√ | get AL L 1 x 1 x 3/32 x (12+4) | for battery box reinforcement
√ | reinforce battery edges @ cage tabs
√ | reinstall battery (tilted fwd) | 3/32 tabs on back. Relieves pressure on skin
√ | bundle & hang cable harness
√ | key switch circuit: harden (+12V!) | this may have caused the BMS damage
√ | kickstand circuit: shorten, harden | move switch to comm panel. Rarely used.
√ | replace Polycarb. nose fork shield
√ | fix, improve fwd charger mount
√ | epoxy 2 missing nose cone nuts | also, switch all screws to phillips heads
√ | straighten crosstube under stick | was bent up 3/8" from nose gear incident
√ | make, install comm panel cover
√ | move static ports forward | pressure too negative in rearward location
√ | change dash mounting | for vetter visibility
√ | epoxy aileron pp tube cage
√ | epoxy luggage box
√ | secure tail prop on cargo box lid | zero g?
√ | replace USB cable for tablet
√ | replace USB cable for iPod
√ | replace iPod | better battery life
√ | door pin from below | to allow removal with wing installed
√ | better strobes | new Kuntzleman xenon strobes seem OK
√ | install accoustic mat under turtledeck | …and inside cowling
√ | reinforce door sill
√ | improve throttle lever action | constant friction thru range
√ | repair belly fiberglass | holes, cracks from nose gear incident
√ | paint nose cone ? | black nose not a good look
√ | strip, cover rudder | UV damage. Materials under warranty
√ | recalibrate Cycle Analyst | using ammeter, compare to Zero app